## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
BMS Design
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-04-21 |  |  |  |  | April | [13 empty] | May | [27 empty] | June
Scrolling Increment: | 0 | time axis 2022-04-21 to 2022-06-15
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-04-21 to 2022-06-15
Milestones
Research Paper | Milestone | Ethan & Patrick |  | 2022-05-15 | 1 | bar: 2022-05-15
Final Report | Milestone | Ethan & Patrick |  | 2022-05-30 | 1 | bar: 2022-05-30
Final Presentation | Milestone |  |  | 2022-06-06 | 1 | bar: 2022-06-06
LMU Design
Finalisation of PCB | High Risk | Patrick | 0% | 2022-04-19 | 5
PCB Manufacture | High Risk | Patrick | 0% | 2022-04-24 | 9
Component Order | Med Risk | Patrick | 0% | 2022-04-24 | 7
PCB Assembly | High Risk | Ethan | 0% | 2022-05-03 | 3
PCB Testing & Rectification | Med Risk | Patrick & Ethan | 0% | 2022-05-06 | 21
Final Battery Stack Assembly | High Risk | Patrick | 0% | 2022-05-01 | 4
Code Writing
Basic System Functions (CAN/Heartbeat) | Med Risk | Patrick | 0% | 2022-04-24 | 1
Balance Request Service | High Risk | Ethan | 0% | 2022-04-25 | 14
Active Balance Routine | High Risk | Ethan | 0% | 2022-04-27 | 5
Passive Balance Routine | High Risk | Ethan | 0% | 2022-04-22 | 5
Telemetry Service | High Risk | Patrick | 0% | 2022-04-25 | 1
Cell Monitoring | High Risk | Ethan | 0% | 2022-04-22 | 8

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-04-21 |  |  |  |  | April | [13 empty] | May | [27 empty] | June
Scrolling Increment: | 1 | time axis 2022-04-22 to 2022-06-16
Milestone description | Category | Assigned to | Progress | Start | Days | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
TITLE 1
Task 1 | Goal | Name | 25% | 2022-04-21 | 3 | F: 2; S: 2
Task 2 | Milestone |  |  | 2022-04-26 | 1 | bar: T
Task 3 | Low Risk |  | 50% | 2022-04-18 | 10
Task 4 | Milestone |  |  | 2022-05-11 | 1 | bar: W
Task 5 | Med Risk |  | 10% | 2022-04-27 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2022-04-27 | 13
Task 2 | On Track |  | 50% | 2022-04-29 | 9
Task 3 | Low Risk |  | 33% | 2022-05-04 | 11
Task 4 | Milestone |  |  | 2022-05-06 | 1 | bar: F
Task 5 |  |  |  | 2022-05-07 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-05-06 | 4
Task 2 | Med Risk |  |  | 2022-05-09 | 14
Task 3 | On Track |  |  | 2022-05-24 | 6
Task 4 | Goal |  |  | 2022-05-28 | 3 | S: 2; S: 2; M: 2
Task 5 | Low Risk |  |  | 2022-04-27 | 19
TITLE 4
Task 1 |  |  |  | 2022-05-31 | 15
Task 2 |  |  |  | 2022-06-14 | 5
Task 3 | Milestone |  |  | 2022-07-26 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-04-21 |  |  |  |  | April | [6 empty] | May | [34 empty] | June
Scrolling Increment: | 5 | time axis 2022-04-26 to 2022-06-20
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-04-26 to 2022-06-20
TITLE 1
Task 1 | Goal | Name | 25% | 2022-04-21 | 3
Task 2 | Milestone |  |  | 2022-04-26 | 1 | bar: 2022-04-26
Task 3 | Low Risk |  | 50% | 2022-04-18 | 10
Task 4 | Milestone |  |  | 2022-05-11 | 1 | bar: 2022-05-11
Task 5 | Med Risk |  | 10% | 2022-04-27 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2022-04-27 | 13
Task 2 | On Track |  | 50% | 2022-04-29 | 9
Task 3 | Low Risk |  | 33% | 2022-05-04 | 11
Task 4 | Milestone |  |  | 2022-05-06 | 1 | bar: 2022-05-06
Task 5 |  |  |  | 2022-05-07 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-05-06 | 4
Task 2 | Med Risk |  |  | 2022-05-09 | 14
Task 3 | On Track |  |  | 2022-05-24 | 6
Task 4 | Goal |  |  | 2022-05-28 | 3 | 2022-05-28: 2; 2022-05-29: 2; 2022-05-30: 2
Task 5 | Low Risk |  |  | 2022-04-27 | 19
TITLE 4
Task 1 |  |  |  | 2022-05-31 | 15
Task 2 |  |  |  | 2022-06-14 | 5
Task 3 | Milestone |  |  | 2022-07-26 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one